## Sheet1
Datum | Teamlid | Domein | Taak | Tijd (in uur)
2017-11-14 | Pieter | DES | Create productie dossier : Discover (Briefing), Define (analyse) | 3
2017-12-23 | Pieter | DEV | Creatie VUE app: installatie pakketten | 5
2017-12-24 | Pieter | DEV | Opzetten Drupal site | 4
2017-12-26 | Pieter | DEV | Login Vue app | 4
2017-12-27 | Pieter | DEV | Bike instantie aanmaken. Content Creatie. Axios pakket toevoegen. REST | 5
2017-12-28 | Pieter | DEV | Bike Overview page | 4
2017-12-29 | Pieter | DEV | Bike Detail page, Google maps + Open data laadpunten Gent | 8
2017-12-30 | Pieter | DEV | User Page + reservatie canceling | 5
2017-12-31 | Pieter | DEV | HTML pages drupal theme + drupal theming | 7
2018-01-05 | Pieter | DES | Update productie dossier | 4
2018-01-06 | Pieter | DES | Update productie dossier | 4
2018-08-05 | Pieter | DEV | FULL RESET: creating a new drupal site / installing modules | 8
2018-08-06 | Pieter | DEV | Drupal - setting up a new drupal Theme - styling HTML template - installing sass | 8
2018-08-07 | Pieter | DEV | drupal: - Setting Up my HTML template to be immersive with the drupal components/regions | 9
2018-08-08 | Pieter | DEV | drupal: - finishing up contact form - setting up rest-api - responseniss - home - FAQ - contact Vue: - setting up project - Learning Vuex - setting up: Vuex / vue-routing / vue-session / sass | 8
2018-08-09 | Pieter | DEV | VUE - Basic pages set-up - drawer nav set-up | 6
2018-08-10 | Pieter | DES | Update productie dossier | 5
2018-08-11 | Pieter | DEV | VUE - styling bikes overview page - styling drawer nav - dynamic routing set-up on bike detail page | 8
2018-08-12 | Pieter | DEV | Drupal - adding “available” en “rented by” field to ebike content VUE - styling details page - setting up “my reservations” page | 8
2018-08-13 | Pieter | DEV | VUE - Leaflet maps integration - creating map pin - adding open data gent for charging points ebike - reservations page - account page - Getting Patch api request working | 10
2018-08-14 | Pieter
2018-08-15 | Pieter
2018-08-16 | Pieter
Totaal |  |  |  | 123